## Slide 1: Project summary
ATTRITIONAL FIRE RISK
                To build a system that estimates level risk of a loss from non-catastrophic fire based on measurable property attribute. Estimating risk includes two variables, better predicted by two separate models:
                Chance of event happening
                Damage incurred if event happens
                Data available:
                Attributes and fire outcomes for 100k properties
                Aerial images of same properties
                Fire station locations and capabilities
                Missing data to be collected:
                Attributes for properties without fires in similar areas as the dataset above
                Whole system to be deployed to production within Zesty.ai’s infrastructure

## Slide 2: Draft workplan
ATTRITIONAL FIRE RISK
W1
W2
W3
W4
W5
W6
W7
W8
W9
W10
W11
W12
W13
End-to-end model track
Review and setup
Epic
Model serving API
Data collection
Integrated testing
Requirements mapping
Request handling API
Expected fire outcome
Compute provisioning
Chimney detection
Data profiling
Chance of fire
Preparation
Modeling
Deployment and integration
Ongoing updates
Ongoing updates
Markers indicate when a preliminary, working version of model is expected. In the case of end-to-end, track may be dropped if milestone not reached in 4 weeks.

## Slide 3: Tasks and resources
ATTRITIONAL FIRE RISK
(1) All resources allocated 100% at task for duration of timeline unless otherwise noted
Group | Epic | Key tasks | Resources(1) | Timeline
Preparation | Requirements mapping | Specify how model will be used (access points, frequency, limitations, security) Choose performance metrics Estimate compute resource requirements | 1 Product Mgr, 50% Touchpoints with clients, MLEs, Product and Engineering | 2 weeks
 | Data collection | Gather and store attribute dataset for properties without fires Label chimneys on aerial images (outsource if no programmatic solution) | 1 Data Scientist or MLE Outsource labeling (TBC) | 2 weeks
 | Data profiling | Create overview of features and images Look for failure points: potential bias, poor imputations, questionable values | 2 MLEs, 50% | 2 weeks (+ ongoing updates)
 | Compute provisioning | Provision cloud instances for model training as per requirements mapping above | 1 DevOps or SW Engineer | 1 week
 | Review and setup | Review state-of-the-art ML literature Setup tools and virtual environments | 2 MLEs, 50% | 2 weeks (+ ongoing updates)
Modeling | End-to-end model track | Iterative development process of writing code and training different model architectures to predict chance of fire and estimate effects from raw features (attributes, images, fire stations) | 1 MLE | 10 weeks
 | Chimney detection | Iterative development process of writing code and training different model architectures to detect chimneys from aerial image | 1 MLE | 5 weeks
 | Chance of fire | Iterative development process of writing code and training different model architectures to estimate chance of fire, based on attributes and detection of chimney | 1 MLE, 50% | 5 weeks
 | Expected fire outcome | Iterative development process of writing code and training different model architectures to estimate fire outcome, based on attributes, detection of chimney, and fire station data | 1 MLE, 50% | 5 weeks
Deployment and integration | Request handling API | Develop and deploy server application to receive and process inference requests (queueing if necessary) Code call from this application to model serving API | 1 SW Engineer | 2 weeks
 | Model serving API | Develop and deploy server application to receive data and run inferences with the models Code return of model results to request handling API | 1 SW Engineer | 2 weeks
 | Integrated testing | Validate that all parts of the system work well together, including models. Design and run stress test scenarios | 1 QA or SW Engineer | 3 weeks

## Slide 4: Risk assessment
Risk | Preventive measures
Unclear performance metric | Coordinate with end users as early as possible, and frequently during development Structure communication to guide stakeholders towards agreement
Data collection delay | Use dummy data to advance work in parallel Enrich dataset (especially regarding labeling images, where it is possible to make up decent images with precisely positioned fake chimneys)
Data limitations (e.g. bias) | Testing preliminary models as soon as possible
Slow progress on end-to-end model | Abandon track after 4 weeks if no working model
Models performance drop in production | Run production data pipeline as early as possible and map differences to training data
Model degradation over time | Monitor model performance constantly Have scripts and documentation ready for model retraining
Poor user understanding of how to use product | Prepare user success initiatives such as training workshops

## Slide 5: Delayed work scenario – action plan
                Considering the workplan presented above, last 4 weeks are expected to focus on finishing models and deployment applications.
                Second-to-last week before deployment (no models finished, model serving API not finished):
                Notify all stakeholders that project will be deployed at “80% complete” stage
                Abandon end-to-end model track and fully assign 1 MLE for each of the other outstanding models
                Provision additional compute capacity to accelerate model training
                Request additional Software Engineer to start integrated testing of current systems at whatever stage available
                Last week before deployment (preliminary working models available, both APIs ready):
                Validate integration between applications within expected normal scenarios with 2 Software Engineers
                Package preliminary models for deployment
                First week after deployment:
                Continue training models with similar architecture as deployed – replace if significant improvement
                Stress test integration
                Second week after deployment:
                Finalize model training and replace with best version
                Notify stakeholders that system has been finalized

## Slide 6: Questions
ATTRITIONAL FIRE RISK
                What are the key sets of activities that need to be completed to get the project assembled and out into production? Please be as detailed as possible and think about the entire production process. See pages 2-3
                What are the key milestones or checkpoints throughout the project? See pages 2-3
                What are the major risks that you could encounter to getting the production out on time? See page 4
                How would you track progress with various members / functions of teams you’re collaborating with? By organizing weekly sprints and keeping a board of tasks to be completed. Online tools are preferable since the team is split across several locations – Trello/JIRA being the most relevant example. Daily 5-10 min touchpoints with each team (ML / Eng.) to share progress and surface roadblocks.
                2 weeks before deployment, you realize that there’s a month of outstanding work to be done. What is your action plan? Please be very specific when talking about deadlines and activities. See page 5